{"text_format":"1","workbook":"xlsx","n_sheets":2,"sheets":["Sheet1","Sheet2"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":8,"n_cols":18,"rows_kept":8,"cut":false,"hidden":false,"merged":[[8,4,10,17]]}
[]
[null,null,null,null,"2021-10-31",{"$f":"E2+1","v":"2021-11-01"},{"$f":"F2+1","v":"2021-11-02"},"2021-11-03","2021-11-04","2021-11-05","2021-11-06","2021-11-07","2021-11-08","2021-11-09","2021-11-10","2021-11-11","2021-11-12","2021-11-13"]
[null,"項目","開始日","完了日",{"$f":"TEXT(E2,\"aaa\")","v":"日"},{"$f":"TEXT(F2,\"aaa\")","v":"月"},"火","水","木","金","土","日","月","火","水","木","金","土"]
[null,"足場組立","2021-11-01","2021-11-02",{"$f":"IF(AND(E$2>=$C4,E$2<=$D4),\"■\",\"\")","v":""},{"$f":"IF(AND(F$2>=$C4,F$2<=$D4),\"■\",\"\")","v":"■"},"■","","","","","","","","","","",""]
[null,"外壁塗装","2021-11-03","2021-11-07",{"$f":"IF(AND(E$2>=$C5,E$2<=$D5),\"■\",\"\")","v":""},"","","■","■","■","■","■","","","","","",""]
[null,"検査","2021-11-07","2021-11-09","","","","","","","","■","■","■","","","",""]
[null,"足場撤去","2021-11-10","2021-11-11","","","","","","","","","","","■","■","",""]
[null,null,null,null,{"$f":"COUNTIF(E4:E7,\"■\")","v":0},{"$f":"COUNTIF(F4:F7,\"■\")","v":1},1,1,1,1,1,2,1,1,1,1,0,0]

{"sheet":"Sheet2","index":1,"n_rows":7,"n_cols":18,"rows_kept":7,"cut":false,"hidden":false,"merged":[]}
[]
[null,null,null,null,"2021-10-31",{"$f":"E2+1","v":"2021-11-01"},{"$f":"F2+1","v":"2021-11-02"},"2021-11-03","2021-11-04","2021-11-05","2021-11-06","2021-11-07","2021-11-08","2021-11-09","2021-11-10","2021-11-11","2021-11-12","2021-11-13"]
[null,"項目","開始日","完了日",{"$f":"TEXT(E2,\"aaa\")","v":"日"},{"$f":"TEXT(F2,\"aaa\")","v":"月"},"火","水","木","金","土","日","月","火","水","木","金","土"]
[null,"足場組立","2021-11-01","2021-11-02"]
[null,"外壁塗装","2021-11-03","2021-11-07"]
[null,"検査","2021-11-07","2021-11-09"]
[null,"足場撤去","2021-11-10","2021-11-12"]